## Civil Works Progress
OIL INDIA LIMITED — DULIAJAN WELL-SITE — CIVIL WORKS PROGRESS
Reporting Period: Mar-Dec 2026 ¦ Sheet generated for progress review
Identification |  |  | Work Description |  |  | Schedule |  | Progress
Activity ID | Tag / Ref | WBS Level | Work Item | Discipline | Location | Commenced | Actual / Est. Completion | Planned Qty | Achieved Qty
CIV-BLD-1161 | — | L5 | Control building blockwork and roofing | CIV | Substation | 19/05/2026 | 2026-06-01 | 145 | 145
CIV-DRA-1014 | — | L5 | Precast drain construction, Unit 1 wellhead periphery | CIV |  | 2026-04-06 | 15/04/2026 | 260 | 260
CIV-DRA-1051 | — | L5 | Roadside drain slabs, approach road | CIV | Manifold | 2026-03-14 |  | 380 | 380
CIV-EXC-1003 | — | L5 | Cut and fill to formation level, well pad Unit 1 | CIV | Unit 2 | 20/Mar/2026 | 31/03/2026 | 2400 | 2400
CIV-EXC-1020 | — | L5 | Bulk excavation, Unit 2 wellhead cellar | CIV | Tank Farm | 23/03/2026 |  | 1600 | 1600
CIV-EXC-1031 | — | L5 | Rock breaking and muck disposal, flare stack base FST-1301 | CIV | Unit 2 | 2026-03-30 | 03/04/2026 | 140 | 140
CIV-EXC-1115 | — | L5 | Excavation for foundations V-2101 and WHCP-2101, Unit 2 | CIV | Unit 2 | 08/Apr/2026 | 2026-04-14 | 580 | 580
CIV-FDN-1106 | V-1101 | L5 | Non-shrink grouting, separator skid base ring V-1101 | CIV | Workshop |  | 16/May/2026 | 1.2 | 1.2
CIV-FDN-1108 | V-1201 | L6 | Anchor bolt template survey and setting, V-1201 | CIV | Tank Farm | 2026-04-24 | 25/04/2026 | 16 | 16
CIV-FDN-1118 | V-2101 | L6 | 7-day wet cure, V-2101 foundation | CIV | Tank Farm | 23/04/2026 | 30/Apr/2026
CIV-FDN-1126 | — | L5 | Flare stack foundation and guy anchor blocks, FST-1301 | CIV | Manifold | 06/Apr/2026 | 11/04/2026 | 38 | 38
CIV-FDN-1127 | FST-1301 | L5 | Anchor bolts and template, flare stack FST-1301 | CIV | Tank Farm | 10/Apr/2026 | 11/Apr/2026 | 20 | 20
CIV-FDN-1152 | TK-2102 | L5 | Ring wall foundation, storage tank TK-2102 | CIV | Unit 1 | 17/04/2026 | 25/Apr/2026 | 110 | 110
CIV-FDN-1153 | OWS-2201 | L5 | Oil-water separator pit civil works, OWS-2201 | CIV | Unit 2 | 13/Apr/2026 | 2026-04-18 | 28 | 28
CIV-FDN-1154 | — | L5 | Dyke wall construction, tank farm bund | CIV |  | 20/04/2026 | 30/Apr/2026 | 210 | 210
CIV-FDN-1167 | — | L5 | Sleeper and column footings, pipe rack Module 3 | CIV |  | 04/May/2026 | 07/May/2026 | 68 | 68
CIV-FLR-1021 | — | L5 | Anti-termite treatment and PCC blinding, Unit 2 pad | CIV | Tank Farm | 2026-04-02 |  | 950 | 950
CIV-FNC-1052 | — | L5 | Fencing, approach road stretch | CIV |  | 2026-04-20 | 2026-04-27 | 420 | 420
CIV-RDS-1012 | — | L6 | Lay and compact WMM course, road U1 Ch 0-160 | CIV | Workshop | 2026-04-14 |  | 160 | 160
CIV-RDS-1013 | — | L6 | Lay and compact WMM course, road U1 Ch 160-320 | CIV | Unit 1 | 2026-04-18 | 22/Apr/2026 | 160 | 160
CIV-RDS-1050 | — | L5 | BC course laying, approach road | CIV | Manifold | 23/Mar/2026 | 27/03/2026 | 400 | 400
CIV-SRV-1001 | — | L5 | Topographic survey and grid establishment, well-site boundary | CIV |  | 02/Mar/2026 | 07/03/2026 | 4800 | 4800
CIV-UGS-1181 | — | L5 | Cable trench with precast covers, Unit 2 to substation | CIV | Workshop | 2026-05-21 | 2026-05-28 | 190 | 190
CIV-UGS-1182 | — | L5 | Trench sand bedding and protection tiles, cable routes | CIV | Substation | 23/05/2026 | 2026-05-27 | 400 | 400
CIV-YRD-1046 | — | L5 | Crusher fines laying, equipment laydown yard | CIV | Manifold | 2026-03-23 | 27/Mar/2026 | 1200 | 1200
CIV-YRD-1054 | — | L5 | Bench marking and centre-line offsets, all areas | CIV | Tank Farm |  | 2026-03-12
Total rows: 26