## Electrical & Instrumentation
OIL INDIA LIMITED — DULIAJAN WELL-SITE — ELECTRICAL & INSTRUMENTATION
Reporting Period: Jun 2026-Feb 2027 ¦ Sheet generated for progress review
Identification |  |  | Work Description |  |  | Schedule |  | Progress
Activity ID | Tag / Ref | WBS Level | Work Item | Discipline | Location | Commenced | Actual / Est. Completion | Planned Qty | Achieved Qty
EL-CBL-1374 | T-1 | L5 | Pull MV cable 11 kV, substation to transformer T-1 | ELE | Manifold | 03/Aug/2026 | 06/Aug/2026 | 180 | 180
EL-CBL-1375 | T-2 | L5 | Pull MV cable 11 kV, substation to transformer T-2 | ELE | Tank Farm | 07/Aug/2026 |  | 180 | 180
EL-CBL-1377 | WHCP-2101 | L5 | Pull LV power cables, wellhead panel WHCP-2101 feeders, Unit 2 | ELE | Tank Farm | 08/Jul/2026 | 2026-07-11 | 260 | 260
EL-CBL-1382 | — | L5 | Glanding and termination, LV panels, substation | ELE | Tank Farm | 01/08/2026 | 07/08/2026 | 84 | 84
EL-CBL-1383 | — | L6 | Cable glanding, MCC-1 and MCC-2 feeders | ELE | Tank Farm | 03/08/2026 |  | 46 | 46
EL-CBL-1384 | — | L6 | Core termination and lacing, MCC-1 and MCC-2 | ELE | Tank Farm | 05/08/2026 | 08/Aug/2026 | 92 | 92
EL-ENS-1530 | — | L5 | Insulation resistance and hi-pot tests, MV cables to T-1 and T-2 | ELE | Substation | 25/Sep/2026 | 2026-09-28 | 6 | 6
EL-ENS-1531 | — | L5 | Protective relay setting and primary injection tests | ELE |  | 29/09/2026 | 02/Oct/2026 | 12 | 12
EL-ENS-1532 | — | L5 | Substation energization | ELE | Unit 2 | 2026-10-12 | 12/Oct/2026
EL-GRD-1378 | — | L5 | Earth grid and earthing pits, site-wide | ELE | Tank Farm |  | 2026-05-27 | 2400 | 2400
EL-SWB-1373 | — | L5 | Install MCC panels and switchboard, substation room | ELE | Substation | 11/07/2026 | 17/07/2026 | 6 | 6
EL-TRF-1372 | T-2 | L5 | Set and terminate transformer T-2, 11/0.433 kV | ELE |  | 2026-08-03 | 05/08/2026 | 1 | 1
EL-TRK-1360 | — | L5 | Install cable tray ladder 600 mm, rack tier 3 | ELE | Manifold | 2026-07-01 | 2026-07-07 | 210 | 210
EL-TRK-1361 | — | L5 | Install cable tray 450 mm, rack tier 3, Unit 2 stretch | ELE | Manifold | 03/07/2026 | 2026-07-07 | 140 | 140
EL-TRK-1362 | — | L5 | Install conduits and flexible connections, Unit 1/2 equipment | ELE |  | 2026-10-29 | 2026-11-02 | 38 | 38
INS-CBL-1396 | JB-101 | L5 | Pull instrument cables, rack tier 2 to junction boxes JB-101 to JB-108 | INS | Unit 1 | 28/Aug/2026 | 03/Sep/2026 | 640 | 640
INS-CHK-1406 | — | L5 | Loop check, Unit 1 loops L-1101 to L-1128 | INS | Unit 1 | 15/Dec/2026 | 19/12/2026 | 28 | 28
INS-CHK-1407 | — | L5 | Loop check, Unit 2 loops L-2101 to L-2122 | INS | Manifold | 07/11/2026 | 11/Nov/2026 | 22 | 22
INS-CHK-1408 | — | L5 | Loop check, tank farm and utilities loops | INS | Tank Farm | 13/11/2026 |  | 16 | 16
INS-CHK-1542 | — | L5 | Integrated ESD and blowdown function test | INS | Workshop |  | 2027-01-03 | 8 | 8
INS-FIT-1392 | LT-1201 | L5 | Install level transmitters LT-1201 to LT-1206, separators | INS | Unit 2 | 2026-06-17 | 20/Jun/2026 | 6 | 6
INS-FIT-1393 | TE-1301 | L5 | Install temperature elements TE-1301 to TE-1312 | INS | Substation |  |  | 12 | 12
INS-FIT-1394 | FE-1401 | L5 | Install flow meter elements FE-1401 to FE-1408, Unit 2 | INS |  | 2026-11-02 | 05/11/2026 | 8 | 8
INS-JBX-1395 | JB-101 | L5 | Install junction boxes JB-101 to JB-108, field | INS |  | 2026-08-24 | 27/08/2026 | 8 | 8
INS-TER-1398 | JB-101 | L5 | Terminate field instruments at JB-101 to JB-108 | INS | Workshop | 2026-09-10 | 18/Sep/2026 | 168 | 168
INS-TRK-1363 | — | L5 | Install instrument cable tray 300 mm, rack tier 2 | INS | Unit 2 |  | 10/Jul/2026 | 180 | 180
Total rows: 26