## Static Equipment Progress
OIL INDIA LIMITED — DULIAJAN WELL-SITE — STATIC EQUIPMENT PROGRESS
Reporting Period: May 2026-Feb 2027 ¦ Sheet generated for progress review
Identification |  |  | Work Description |  |  | Schedule |  | Progress
Activity ID | Tag / Ref | WBS Level | Work Item | Discipline | Location | Commenced | Actual / Est. Completion | Planned Qty | Achieved Qty
STA-DRY-1521 | TK-2101 | L5 | Water fill and settlement check, TK-2101 | STA | Substation | 30/09/2026 | 05/Oct/2026 | 940 | 940
STA-DRY-1522 | TK-2102 | L5 | Water fill and calibration strapping, TK-2102 | STA | Substation |  | 2026-09-23 | 1010 | 1010
STA-FLR-1220 | FST-1301 | L5 | Shop assemble flare stack sections, FST-1301 | STA | Tank Farm | 2026-04-22 | 2026-04-28 | 22 | 22
STA-FLR-1221 | FST-1301 | L5 | Erect flare stack FST-1301, guys tensioned | STA | Tank Farm | 30/Apr/2026 | 2026-05-02 | 1 | 1
STA-FLR-1222 | V-1401 | L5 | Set flare knockout drum V-1401 | STA |  |  | 2026-04-23 | 1 | 1
STA-FLR-1223 | FST-1301 | L5 | Install flare tip and molecular seal, FST-1301 | STA | Substation | 2026-05-04 | 05/05/2026 | 1 | 1
STA-FLS-1526 | FST-1301 | L5 | Flare pilot ignition and pilot line purge test | STA | Unit 1 | 2026-11-05 | 2026-11-05 | 1 | 1
STA-INT-1213 | V-2101 | L5 | Load and fit internals and demisters, V-2101 | STA | Unit 2 | 2026-05-11 | 13/05/2026 | 1 | 1
STA-MCH-1240 | P-1401A | L5 | Set crude transfer pumps P-1401A and P-1401B | STA | Manifold |  | 28/05/2026 | 2 | 2
STA-MCH-1241 | P-1401A | L5 | Alignment check, P-1401A/B couplings | STA | Unit 2 | 2026-05-28 | 2026-05-29 | 2 | 2
STA-MCH-1242 | P-1401A | L5 | Motor mounting and bolt torque, P-1401A/B | STA | Tank Farm | 2026-05-29 | 30/05/2026 | 2 | 2
STA-MS-1556 | — | L5 | First crude transfer to TK-2101 | STA |  | 22/Feb/2027 | 2027-02-22
STA-PRS-1520 | V-1101 | L5 | Tightness and pressure test, separators V-1101 and V-1201 | STA | Unit 2 | 04/11/2026 | 05/11/2026 | 2 | 2
STA-ROT-1524 | P-1401A | L5 | Performance run, crude transfer pumps P-1401A/B | STA | Tank Farm | 27/09/2026 | 28/Sep/2026 | 2 | 2
STA-SET-1200 | V-1101 | L5 | Receive and stage separator V-1101, transport from laydown | STA | Unit 1 | 2026-06-06 | 08/06/2026 | 1 | 1
STA-SET-1202 | V-1101 | L5 | Plumb, alignment and bolt torque, V-1101 | STA | Workshop | 11/Jun/2026 | 2026-06-11 | 1 | 1
STA-SET-1203 | V-1201 | L5 | Rig and set glycol contactor V-1201 | STA | Manifold | 12/06/2026 | 2026-06-15 | 1 | 1
STA-SET-1204 | — | L5 | Set production manifold header assemblies, Unit 1, 16"-P-1002-A1A tie- | STA | Substation | 05/05/2026 | 09/05/2026 | 38 | 38
STA-SET-1207 | — | L5 | Set fuel gas skid, utilities plinth U1 | STA | Unit 2 | 15/Jun/2026 | 16/06/2026 | 1 | 1
STA-SET-1211 | V-2201 | L5 | Set test separator V-2201, Unit 2 | STA | Workshop | 30/Apr/2026 | 2026-05-01 | 1 | 1
STA-SET-1244 | — | L5 | Monorail and davit erection, separator platforms | STA | Workshop | 2026-06-13 | 2026-06-16 | 1 | 1
STA-TNK-1230 | TK-2101 | L5 | Tank shell erection, courses 1-3, TK-2101 | STA | Manifold |  | 2026-06-05 | 46 | 46
STA-TNK-1231 | TK-2101 | L6 | Shell courses 1-2, tank TK-2101 | STA | Unit 2 | 25/May/2026 | 31/05/2026 | 30 | 30
STA-TNK-1235 | TK-2102 | L5 | Internal floating roof assembly, TK-2102 | STA |  | 2026-05-17 | 21/May/2026 | 9 | 9
STA-TNK-1236 | — | L5 | Tank nozzles and manways fitting, TK-2101 and TK-2102 | STA | Manifold | 09/06/2026 |  | 18 | 18
STA-WLD-1205 | — | L6 | Field welds, Unit 1 manifold spools, welds 1-12 | STA | Tank Farm | 08/May/2026 | 11/May/2026 | 12 | 12
Total rows: 26