## Piping Progress
OIL INDIA — DULIAJAN WELL-SITE DEVELOPMENT — PIPING PROGRESS REGISTER
Reporting Period: Aug-Sep 2026 ¦ Contractor: ABC Infra Pvt Ltd
Identification |  |  | Work Description |  |  | Schedule |  |  | Progress
Line No. | Tag/Spool | Test Section | Activity Name | Discipline Code | Location | Start Date | End Date | Planned Duration (days) | % Done | Status | Remarks / JMR Ref
PIP-1023 | P-RACK-T1 | — | Pipe Rack Steel Erection Tier 1 | PIP | Main Rack | 2026-07-13 | 25/07/2026 | 12 | 100 | Completed
PIP-1024 | P-RACK-T2 | — | Pipe Rack Steel Erection Tier 2 | PIP | Main Rack | 22/07/2026 | 02/08/2026 | 11 | 97 | In Progress | 4 MT remaining, crane issue
PIP-1025 | 24"-P-1001-A1A | — | Spool Fab — 24" Main Header | PIP | Workshop | 15/Jul/2026 | 2026-08-05 | 21 | 100 | Complete | 18 spools fabricated
PIP-1026 | 12"-P-1002-B1A | — | Spool Fab — 12" Transfer Line | PIP | Workshop | 18/Jul/2026 | 01/08/2026 | 14 | 100 | Complete | 12 spools completed
PIP-1027 | 8"-P-1003-A1B | — | Spool Fab — 8" Flare Header | PIP | Workshop | 20/Jul/2026 | 2026-08-08 | 19 | 71 | In Progress | 10 of 14 spools done
PIP-1028 | 4"-P-1010-C1A | — | Spool Fab — 4" Utility Water | PIP | Workshop | 25/Jul/2026 | 10/08/2026 | 16 | 100 | Complete | 8 spools done
PIP-1029 | 6"-P-1015-A1A | — | Spool Fab — 6" Drain Header | PIP | Workshop | 28/Jul/2026 | 2026-08-12 | 15 | 20 | In Progress | 2 of 10 spools done
PIP-1030 | 24"-P-1001-A1A | TS-01 to TS-06 | Spool Erection — 24" Main Header | PIP | Tier 1 Rack | 01/08/2026 | 18/08/2026 | 17 | 100 | Complete | All 18 spools erected
PIP-1031 | 12"-P-1002-B1A | TS-07 to TS-10 | Spool Erection — 12" Transfer | PIP | Tier 1 Rack | 02/08/2026 | 15/08/2026 | 13 | 100 | Complete | 12 spools erected
PIP-1032 | 8"-P-1003-A1B | TS-11 to TS-15 | Spool Erection — 8" Flare Header | PIP | Tier 1/2 | 06/08/2026 | 22/08/2026 | 16 | 100 | Complete | 14 spools erected
PIP-1033 | 4"-P-1010-C1A | TS-16 to TS-18 | Spool Erection — 4" Utility Water | PIP | Tier 1 Rack | 11/08/2026 | 22/08/2026 | 11 | 100 | Complete | 8 spools erected
PIP-1034 | 6"-P-1015-A1A | TS-19 to TS-21 | Spool Erection — 6" Drain Header | PIP | Tier 1 Rack | 13/08/2026 | 25/08/2026 | 12 | 100 | Complete | 10 spools erected
PIP-1035 | 24"-P-1001-A1A | — | Flange Mgmt — 24" Main Header | PIP | Tier 1 Rack | 2026-08-19 | 2026-08-26 | 7 | 100 | Complete | 36 flanges bolted
PIP-1036 | 12"-P-1002-B1A | — | Flange Mgmt — 12" Transfer | PIP | Tier 1 Rack | 2026-08-16 | 22/08/2026 | 6 | 100 | Complete | 24 flanges done
PIP-1037 | 8"-P-1003-A1B | — | Flange Mgmt — 8" Flare Header | PIP | Tier 1/2 | 2026-08-23 | 30/08/2026 | 7 | 100 | Complete | 28 flanges bolted
PIP-1038 | 4"-P-1010-C1A | — | Flange Mgmt — 4" Utility Water | PIP | Tier 1 Rack | 2026-08-23 | 28/08/2026 | 5 | 100 | Complete | 16 flanges done
PIP-1039 | 6"-P-1015-A1A | — | Flange Mgmt — 6" Drain Header | PIP | Tier 1 Rack | 2026-08-26 | 02/09/2026 | 7 | 100 | Complete | 20 flanges bolted
PIP-1040 | 24"-P-1001-A1A | HT-01 to HT-06 | Hydrotest — 24" Main Header | PIP | Tier 1 Rack | 2026-08-27 | 03/09/2026 | 7 | 100 | Complete | All 6 sections passed
PIP-1041 | 12"-P-1002-B1A | HT-07 to HT-10 | Hydrotest — 12" Transfer | PIP | Tier 1 Rack | 23/08/2026 | 28/08/2026 | 5 | 100 | Complete | 4 sections passed
PIP-1042 | 8"-P-1003-A1B | HT-11 to HT-15 | Hydrotest — 8" Flare Header | PIP | Tier 1/2 | 2026-08-31 | 06/09/2026 | 6 | 100 | Complete | 5 sections passed
PIP-1043 | 4"-P-1010-C1A | HT-16 to HT-18 | Hydrotest — 4" Utility Water | PIP | Tier 1 Rack | 2026-08-29 | 03/09/2026 | 5 | 100 | Complete | 3 sections passed
PIP-1044 | 6"-P-1015-A1A | HT-19 to HT-21 | Hydrotest — 6" Drain Header | PIP | Tier 1 Rack | 2026-09-03 | 08/09/2026 | 5 | 100 | Complete | 3 sections passed
PIP-1045 | 24"-P-1001-A1A | — | Insulation — 24" Main Header | PIP | Tier 1 Rack | 2026-09-04 | 14/09/2026 | 10 | 100 | Complete | 120 m2 done
PIP-1046 | 12"-P-1002-B1A | — | Insulation — 12" Transfer | PIP | Tier 1 Rack | 2026-08-29 | 06/09/2026 | 8 | 100 | Complete | 65 m2 done
PIP-1047 | 8"-P-1003-A1B | — | Insulation — 8" Flare Header | PIP | Tier 1/2 | 2026-09-07 | 15/09/2026 | 8 | 62 | In Progress | 50 of 80 m2 done
PIP-1048 | — | — | Paint Coating — Pipe Rack | PIP | Full Rack | 2026-09-01 | 12/09/2026 | 11 | 85 | In Progress | 720 of 850 m2, humidity delay
PIP-1049 | — | — | Pipe Support Install — Tier 1 | PIP | Tier 1 Rack | 2026-08-10 | 25/08/2026 | 15 | 100 | Complete | 145 supports installed
PIP-1050 | — | — | Pipe Support Install — Tier 2 | PIP | Tier 2 Rack | 2026-08-15 | 28/08/2026 | 13 | 97 | In Progress | 3 rejected for elevation
PIP-1051 | CS-01 | — | Skid Piping — CS-01 | PIP | CS-01 Skid | 2026-08-05 | 20/08/2026 | 15 | 100 | Complete | 6 spools fab + erect
PIP-1053 | — | — | P&ID Punch List Close-out | PIP | Site-wide | 2026-09-15 | 22/09/2026 | 7 | 67 | In Progress | 8/12 Cat A, 20/28 Cat B closed
TOTAL PIPING DISCIPLINE | [10 empty] | Overall: 22/30 activities complete