## Civil Works Progress
OIL INDIA LIMITED — DULIAJAN — CIVIL & STRUCTURAL PROGRESS TRACKER
Month: August 2026 ¦ Sub-Contractor: BuildRight Construction
Task ID | Work Item | Zone / Location | Commenced | Target Completion | Actual / Est. Completion | Planned Qty | Achieved Qty | UoM | Remarks
CIV-SIT-1001 | Site Clearing Zone A | Zone A | 01/06/2026 | 07/06/2026 | 2026-06-07 | 1200 | 1200 | m2 | Complete
CIV-SIT-1002 | Site Clearing Zone B | Zone B | 03/Jun/2026 | 10/06/2026 | 10/06/2026 | 1200 | 1200 | m2 | Complete
CIV-SIT-1003 | Grading & Compaction A+B | Zone A+B | 11/06/2026 | 2026-06-17 | 2026-06-17 | 2400 | 2400 | m2 | 95% MDD achieved
CIV-PLY-1004 | Bored Piling — Pipe Rack P1-P12 | Main Rack | 18/Jun/2026 | 01/Jul/2026 | 02/Jul/2026 | 16 | 16 | nos | 1 day over, piling rig breakdown
CIV-PLY-1005 | Bored Piling — Equip Fdn EF1-EF4 | Equip Area | 20/06/2026 | 05/Jul/2026 | 2026-07-05 | 24 | 24 | nos | Complete
CIV-PLY-1006 | Bored Piling — Tank TK-1 | Tank Farm | 25/Jun/2026 | 2026-07-12 | 13/07/2026 | 32 | 32 | nos | 1 day over, rain delay
CIV-FDN-1007 | Pedestal Concreting P1-P12 | Main Rack | 02/Jul/2026 | 12/Jul/2026 | 2026-07-12 | 48 | 48 | m3 | M30 concrete, cubes passed
CIV-FDN-1008 | Equip Foundation EF1-EF4 | Equip Area | 06/07/2026 | 2026-07-20 | 20/Jul/2026 | 120 | 120 | m3 | M35 concrete, 7-day strength OK
CIV-FDN-1009 | Tank Ringwall Foundation TK-1 | Tank Farm | 13/Jul/2026 | 2026-07-25 | 2026-07-25 | 65 | 65 | m3 | Complete
CIV-FDN-1010 | Slab-on-Grade Pump House | Pump House | 14/Jul/2026 | 21/Jul/2026 | 21/07/2026 | 180 | 180 | m2 | 200 mm thk M30
CIV-BKL-1011 | Backfilling — Pipe Rack Trenches | Main Rack | 22/Jul/2026 | 2026-07-28 | 28/Jul/2026 | 320 | 320 | m3 | Compacted sand fill
CIV-BKL-1012 | Backfilling — Equipment Pads | Equip Area | 2026-07-21 | 2026-07-28 | 2026-07-28 | 180 | 180 | m3 | Approved backfill material
CIV-BND-1013 | Containment Bund Wall Zone A | Tank Farm | 26/Jul/2026 | 2026-08-08 | 08/Aug/2026 | 85 | 85 | m3 | Complete, 600mm thk RC
CIV-GBM-1014 | Grade Beams Pipe Rack | Main Rack | 15/Jul/2026 | 2026-07-22 | 17/08/2026 | 42 | 42 | m3 | Completed in 2 pours
CIV-DWG-1015 | Drainage Channels Perimeter | Plot Boundary | 01/Aug/2026 | 2026-08-12 | 02/09/2026 | 160 | 160 | lm | Delayed by fencing conflict
CIV-FNC-1016 | Fence & Gate Plot Boundary | Plot Boundary | 2026-08-10 | 18/08/2026 | 02/09/2026 | 480 | 480 | lm | Complete, 3 gates
CIV-PLG-1017 | Firewater Pit Zone B | Zone B | 2026-08-05 | 2026-08-12 | 12/08/2026 | 45 | 45 | m3 | Lined pit complete
CIV-FND-1018 | Foundation — Compressor Skid CS-01 | Equip Area | 08/Jul/2026 | 16/Jul/2026 | 2026-07-16 | 35 | 35 | m3 | M35, curing complete
CIV-FND-1019 | Foundation — Header Skid HS-01 | Equip Area | 10/Jul/2026 | 2026-07-17 | 17/07/2026 | 28 | 28 | m3 | M30, complete
CIV-FLR-1020 | Flooring — MCC Room | MCC Room | 28/Jul/2026 | 03/Aug/2026 | 23/08/2026 | 95 | 95 | m2 | Tiles done. Holiday delays
CIV-PLT-1021 | Plastering & Painting MCC Room | MCC Room | 04/Aug/2026 | 10/Aug/2026 | 08/09/2026 | 220 | 220 | m2 | 2 coats plaster + distemper
CIV-APN-1022 | Cable Tray Buried A+B | Zone A+B | 01/Aug/2026 | 10/Aug/2026 | 2026-09-02 | 280 | 280 | lm | Completed, backfilled
DISCIPLINE TOTAL: CIVIL | [8 empty] | 9 of 22 complete