## HSE & Commissioning Register
OIL INDIA LIMITED — DULIAJAN WELL-SITE — HSE & COMMISSIONING REGISTER
Reporting Period: Mar 2026-Mar 2027 ¦ Sheet generated for progress review
Identification |  |  | Work Description |  |  | Schedule |  | Progress
Activity ID | Tag / Ref | WBS Level | Work Item | Discipline | Location | Commenced | Actual / Est. Completion | Planned Qty | Achieved Qty
HSE-DOC-1551 | — | L5 | As-built markup verification and red-line transfer | HSE | Unit 2 |  | 26/Nov/2026
HSE-DOC-1552 | — | L5 | Compilation of handover dossiers and O&M manuals | HSE | Unit 2 | 2026-11-23 | 02/12/2026
HSE-DOC-1559 | — | L5 | As-built drawing submission and document close-out to OIL | HSE | Manifold | 2027-03-03 | 12/03/2027
HSE-HDO-1554 | — | L5 | RFSU Unit 1 | HSE |  | 04/01/2027 | 2027-01-04
HSE-HDO-1555 | — | L5 | RFSU Unit 2 | HSE | Substation | 2027-02-04 | 04/Feb/2027
HSE-HDO-1557 | — | L5 | Provisional handover to Operations | HSE | Manifold | 2027-02-27 | 27/02/2027
HSE-MS-1500 | — | L5 | Mechanical Completion Unit 1 | HSE | Unit 1 | 31/10/2026 | 31/10/2026
HSE-MS-1501 | — | L5 | Mechanical Completion Unit 2 | HSE | Unit 2 | 09/11/2026 | 09/11/2026
HSE-MS-1502 | — | L5 | Mechanical Completion, Tank Farm and Utilities | HSE | Tank Farm | 2026-09-21 | 21/09/2026
HSE-PSC-1550 | — | L5 | Pre-startup safety review (PSSR) walkthrough | HSE | Tank Farm | 22/Dec/2026 | 24/12/2026 | 1 | 1
HSE-PUN-1558 | — | L5 | Punchlist closure, category A and B items | HSE | Tank Farm | 2027-03-01 | 05/03/2027 | 38 | 38
HSE-REG-1544 | — | L5 | PESO statutory inspection, tanks TK-2101 and TK-2102 | HSE | Unit 1 |  | 12/11/2026 | 2 | 2
HSE-REG-1545 | — | L5 | PESO statutory inspection, flare system and pressure vessels V-1101/V- | HSE | Workshop | 06/Nov/2026 | 09/Nov/2026 | 8 | 8
HSE-REG-1546 | — | L5 | PCB consent and factory inspectorate compliance walkthrough | HSE | Unit 1 | 11/11/2026 | 13/Nov/2026
HSE-SGN-1043 | — | L5 | Safety signage and barricading, phase 1 work fronts | HSE | Tank Farm | 19/03/2026 | 20/03/2026 | 60 | 60
HSE-SGN-1044 | — | L5 | Establish emergency muster points and wind socks | HSE | Manifold | 25/03/2026 | 26/03/2026 | 4 | 4
HSE-TMP-1040 | — | L5 | Erection of temporary site office and stores | HSE | Substation | 2026-03-10 | 16/03/2026 | 180 | 180
HSE-TMP-1041 | — | L5 | Install temporary water supply and septic facility | HSE | Tank Farm | 19/03/2026 | 23/03/2026 | 1 | 1
HSE-TMP-1042 | — | L5 | Temporary power distribution boards and cabling | HSE | Manifold | 2026-03-20 | 23/03/2026 | 1 | 1
HSE-TMP-1053 | — | L5 | Fabrication shed and pipe yard establishment | HSE |  | 2026-03-12 | 17/03/2026 | 640 | 640
HSE-TRN-1553 | — | L5 | Operations training and familiarization, OIL staff | HSE | Unit 1 | 23/12/2026 | 2026-12-27 | 24 | 24
Total rows: 21