## Piping Progress
OIL INDIA LIMITED — DULIAJAN WELL-SITE — PIPING PROGRESS
Reporting Period: Apr 2026-Jan 2027 ¦ Sheet generated for progress review
Identification |  |  | Work Description |  |  | Schedule |  | Progress
Activity ID | Tag / Ref | WBS Level | Work Item | Discipline | Location | Commenced | Actual / Est. Completion | Planned Qty | Achieved Qty
PIP-DRY-1515 | 2"-P-2301-A6A | L5 | Air blowing and drying, instrument air header | PIP | Substation | 2026-11-10 | 11/11/2026 | 1 | 1
PIP-ERC-1301 | — | L5 | Erect rack steel, Module 2 (Ch 40-80) | PIP | Unit 2 | 15/Jun/2026 | 20/06/2026 | 33 | 33
PIP-ERC-1305 | — | L5 | Rack erection, Module 3 tier 1, flare header 18"-P-1301-B7A and utilit | PIP | Workshop | 24/Jun/2026 | 27/Jun/2026 | 29 | 29
PIP-ERC-1311 | 24"-P-1001-A1A | L5 | Erect Line 24"-P-1001-A1A, Unit 2 rack | PIP | Substation | 16/10/2026 | 2026-10-22 | 42 | 42
PIP-ERC-1315 | 16"-P-1002-A1A | L5 | Erect line 16"-P-1002-A1A, gas service, Unit 1 manifold | PIP | Manifold | 2026-11-24 | 28/11/2026 | 54 | 54
PIP-ERC-1316 | 12"-P-1003-A5A | L5 | Erect line 12"-P-1003-A5A, test separator loop | PIP | Workshop | 21/10/2026 | 2026-10-24 | 38 | 38
PIP-ERC-1330 | 18"-P-1301-B7A | L5 | Erect flare header 18"-P-1301-B7A, manifold to KO drum | PIP | Unit 1 | 25/08/2026 | 01/09/2026 | 86 | 86
PIP-ERC-1333 | 6"-P-1302-A6A | L5 | Erect blowdown lines 6"-P-1302-A6A, wellhead SDVs | PIP | Substation | 2026-08-28 | 2026-09-01 | 44 | 44
PIP-ERC-1334 | 4"-P-1303-C5B | L5 | Erect drain header 4"-P-1303-C5B, closed drain | PIP | Substation | 29/08/2026 | 01/09/2026 | 36 | 36
PIP-ERC-1341 | P-1401A | L5 | Suction and discharge piping, pumps P-1401A/B to manifold | PIP | Substation | 28/08/2026 | 03/09/2026 | 58 | 58
PIP-ERC-1343 | 3"-P-2104-C5B | L5 | Install tank dewatering lines 3"-P-2104-C5B | PIP | Tank Farm | 12/06/2026 | 15/Jun/2026 | 22 | 22
PIP-FAB-1310 | 24"-P-1001-A1A | L5 | Shop fabrication, 24"-P-1001-A1A spools | PIP | Substation | 05/Oct/2026 | 13/Oct/2026 | 78 | 78
PIP-FLS-1514 | — | L5 | Flush, dry and reinstate, test packs 1-3 | PIP | Unit 1 |  | 15/Nov/2026 | 12 | 12
PIP-HLT-1325 | 20"-P-2001-A1A | L5 | Pipe supports and guides, Unit 2 rack stretch | PIP | Tank Farm | 26/Oct/2026 | 2026-10-29 | 19 | 19
PIP-HYT-1511 | — | L5 | Hydrotest package 2, Unit 2 header 20"-P-2001-A1A | PIP | Manifold | 2026-11-10 | 12/11/2026 | 3 | 3
PIP-HYT-1512 | 18"-P-1301-B7A | L5 | Pneumatic leak test with nitrogen, flare header | PIP | Substation | 02/Nov/2026 |  | 2 | 2
PIP-INS-1319 | — | L5 | Install restriction orifice spools and sampling connections, Unit 1 | PIP | Unit 1 | 2026-11-27 | 28/11/2026 | 6 | 6
PIP-UGS-1156 | — | L5 | Chamber and catch pit construction, OWS outfall | PIP | Workshop | 2026-04-20 | 2026-04-23 | 3 | 3
PIP-UGS-1170 | 10"-P-1602-B1A | L5 | Trenching for firewater ring main 10"-P-1602-B1A, Unit 1 and manifold | PIP | Substation | 06/04/2026 | 16/Apr/2026 | 480 | 480
PIP-UGS-1172 | 10"-P-1602-B1A | L6 | Hydrotest firewater main 10"-P-1602-B1A, Manifold to Unit 1 section | PIP | Substation | 2026-04-13 | 2026-04-14 | 240 | 240
PIP-UGS-1173 | 10"-P-1602-B1A | L6 | Hydrotest firewater main 10"-P-1602-B1A, Unit 1 to Unit 2 section | PIP | Manifold | 2026-04-15 | 16/04/2026 | 240 | 240
PIP-UGS-1174 | 10"-P-1602-B1A | L5 | Backfill and compaction, firewater trench 10"-P-1602-B1A | PIP | Manifold | 16/04/2026 | 2026-04-21 | 480 | 480
PIP-UGS-1175 | 10"-P-1602-B1A | L5 | Firewater hydrant and monitor bases, ring main 10"-P-1602-B1A | PIP | Unit 2 | 14/Apr/2026 | 2026-04-17 | 8 | 8
PIP-WLD-1313 | — | L5 | Field weld and NDT, crude header rack welds 1-18 | PIP | Substation | 05/Nov/2026 | 2026-11-09 | 18 | 18
PIP-WLD-1332 | — | L5 | Alloy weld and PMI, flare header, welds 20-31 | PIP | Tank Farm | 01/09/2026 |  | 12 | 12
PIP-WLD-1344 | 12"-P-2101-A1A | L5 | Field welds and UT, tank farm manifold, welds 40-52 | PIP | Workshop | 2026-09-17 | 19/Sep/2026 | 13 | 13
Total rows: 26